## Slide 1: Effort and Cost Estimation using COCOMO & TDEV
Team CubeX
Presented by: Vishakha Gupta

## Slide 2: Estimated Effort

## Slide 3: Size of the Product
PHASE | LOC
Mock – up | 1,000 (redundant)
Sprint – 1 | 3,000
Total | 1,000 + 3,000
Total LOC = 4,000

## Slide 4: Using Intermediate COCOMO
Nominal Effort = 3.2 * (KDSI)1.05 person – months
(organic-mode)
STEP – 1
  KDSI = 4
STEP – 2
  Nominal Effort = 3.2 * (4)1.05
STEP – 3
  Nominal Effort = 13.71 person-month

## Slide 5: Using Intermediate COCOMO
NoteIt Effort Multipliers |  |  |  |  |  | 
Cost Drivers | Ratings |  |  |  |  | 
 | VL | L | N | H | VH | EH
Product Attributes |  |  |  |  |  | 
Required Reliability | 0.75 | 0.88 | 1 | 1.15 | 1.4 | 
Database Size |  | 0.94 | 1 | 1.08 | 1.16 | 
Product Complexity | 0.7 | 0.85 | 1 | 1.15 | 1.3 | 1.65
Computer Attributes |  |  |  |  |  | 
Execution Time Constraint |  |  | 1 | 1.11 | 1.3 | 1.66
Main Storage Constraint |  |  | 1 | 1.06 | 1.21 | 1.56
Virtual Machine Volatility |  | 0.87 | 1 | 1.15 | 1.3 | 
Computer Turnaround Time |  | 0.87 | 1 | 1.07 | 1.15 | 
Personnel Attributes |  |  |  |  |  | 
Analyst Capability | 1.46 | 1.19 | 1 | 0.86 | 0.71 | 
Applications Experience | 1.29 | 1.13 | 1 | 0.91 | 0.82 | 
Programmer Capability | 1.42 | 1.17 | 1 | 0.86 | 0.7 | 
Virtual Machine Experience | 1.21 | 1.1 | 1 | 0.9 |  | 
Programming Language Experience | 1.14 | 1.07 | 1 | 0.95 |  | 
Project Attributes |  |  |  |  |  | 
Modern Programming Practices | 1.24 | 1.1 | 1 | 0.91 | 0.82 | 
Use of Software Tools | 1.24 | 1.1 | 1 | 0.91 | 0.83 | 
Required Development Schedule | 1.23 | 1.08 | 1 | 1.04 | 1.1 | 

## Slide 6: Using Intermediate COCOMO
Step – 4
  Nominal Effort = 13.71 person-month
  Effort Multiplier = 1.15*0.94*1*1.11*1*1*0.87*1.46*
  0.91*1*1.1*1*0.91*1*1
  Product of Effort Multiplier = 1.38
  Estimated Effort for project = 13.71 * 1.38 person-month

## Slide 7: Estimated Effort
  Estimated Effort for Project =
  75.72 person-hour

## Slide 8: Actual Effort

## Slide 9
PHASE | LOC
Mock – up | 1,000 (redundant)
Sprint – 1 | 3,500
Total | 1,000 + 3,500
Total LOC = 4,500

## Slide 10: Expected time by Team Members
Phase 1 | Asif | Vishakha | Ayushi | Farha | Kunal | Pallavi
Meetings | 15 | 15 | 15 | 15 | 15 | 15
Presentation | 20 | 20 | 20 | 20 | 20 | 20
Planning | 15 | 15 | 0 | 0 | 15 | 0
UI Design | 0 | 10 | 20 | 10 | 0 | 20
Dev. | 30 | 0 | 10 | 30 | 0 | 0
Testing | 0 | 20 | 0 | 0 | 20 | 10
Documentation | 0 | 0 | 15 | 5 | 10 | 15
Total | 80 | 80 | 80 | 80 | 80 | 80
Total Hours / Person : 80
Total Weeks : 8
Hours / Week : 10

## Slide 11: Expected time by Team Members
Chart: 
| Meetings | Presentation | Planning | UI Design | Dev. | Testing | Documentation
Asif | 15 | 20 | 15 | 0 | 30 | 0 | 0
Vishakha | 15 | 20 | 15 | 10 | 0 | 20 | 0
Ayushi | 15 | 20 | 0 | 20 | 10 | 0 | 15
Pallavi | 15 | 20 | 0 | 10 | 30 | 0 | 5
Kunal | 15 | 20 | 15 | 0 | 0 | 20 | 10
Farah | 15 | 20 | 0 | 20 | 0 | 10 | 15

## Slide 12: Actual time given by Team Members
Phase 1 | Asif | Vishakha | Ayushi | Farha | Kunal | Pallavi
Meetings | 12 | 12 | 12 | 12 | 12 | 12
Presentation | 20 | 20 | 20 | 20 | 20 | 20
Planning | 15 | 15 | 0 | 0 | 10 | 0
UI Design | 0 | 0 | 20 | 30 | 0 | 10
Dev. | 45 | 0 | 18 | 0 | 0 | 10
Testing | 0 | 30 | 0 | 6 | 25 | 0
Documentation | 0 | 0 | 13 | 10 | 17 | 15
Total | 92 | 77 | 83 | 78 | 84 | 67
Total Hours / Person : 80 (approx.)

## Slide 13: Actual time given by Team Members
Chart: 
| Meetings | Presentation | Planning | UI Design | Dev. | Testing | Documentation
Asif | 12 | 20 | 15 | 0 | 45 | 0 | 0
Vishakha | 12 | 20 | 15 | 0 | 0 | 30 | 0
Ayushi | 12 | 20 | 0 | 20 | 18 | 0 | 13
Pallavi | 12 | 20 | 0 | 30 | 0 | 6 | 10
Kunal | 12 | 20 | 10 | 0 | 0 | 25 | 17
Farah | 12 | 20 | 0 | 10 | 10 | 0 | 15

## Slide 14
Chart: 
| Meetings | Presentation | Planning | UI Design | Dev. | Testing | Documentation
Asif | 15 | 20 | 15 | 0 | 30 | 0 | 0
Vishakha | 15 | 20 | 15 | 10 | 0 | 20 | 0
Ayushi | 15 | 20 | 0 | 20 | 10 | 0 | 15
Pallavi | 15 | 20 | 0 | 10 | 30 | 0 | 5
Kunal | 15 | 20 | 15 | 0 | 0 | 20 | 10
Farah | 15 | 20 | 0 | 20 | 0 | 10 | 15
Chart: 
| Meetings | Presentation | Planning | UI Design | Dev. | Testing | Documentation
Asif | 12 | 20 | 15 | 0 | 45 | 0 | 0
Vishakha | 12 | 20 | 15 | 0 | 0 | 30 | 0
Ayushi | 12 | 20 | 0 | 20 | 18 | 0 | 13
Pallavi | 12 | 20 | 0 | 30 | 0 | 6 | 10
Kunal | 12 | 20 | 10 | 0 | 0 | 25 | 17
Farah | 12 | 20 | 0 | 10 | 10 | 0 | 15

## Slide 15: Comparison between predicted and actual

## Slide 16: Comparison Between Actual and Predicted
Difference between actual and predicted
= 80 – 75.72
= 4.28 man-hour

## Slide 17: TDEV

## Slide 18
TDEV = 3*(PM)(0.33 + 0.2*(B – 1.01))
PM = 18.91 person-month
(calculated earlier by COCOMO)
B is the complexity related exponent
  Precedendentedness = 4
  Development Flexibility = 3
  Architecture/Risk resolution = 4
  Team Cohesion = 3
  Process Maturity = 3

## Slide 19
Some of the above values is 17
B = 17/100 + 1.01
= 1.18
TDEV = 3*(18.91)(0.33 + 0.2*(1.18 – 1.01))
= 5 (approx.)

## Slide 20
Thank You!